## Sheet1
Risk | Likelihood | Severity | Mitigation
Github servers go down - All code is stored on a github repo, and would be unaccessible if github servers crashed. | Unlikely | Moderate | All files are also being stored on local computers, and should Github crash, we have a backup copy of files.
Group member computer crashes - We are all using our personal computers, and should one of our computers crash we would be unable to continue working on it. | Possible | Moderate | All files are stored in the Github repo, and should a computer crash, files can be recovered, and the group member can continue working from a school computer.
Group member becomes sick/drops class - We are committed to our group of 5, and would be in trouble if one of our members could no longer continue working with us. | Unlikely | Severe | Should we be forced to lose a group member, we will discuss with Dr. Profetta the possibility of switching to the 4 person project. In the event that he will not allow this, we will divide the work of the member that dropped among the remaining 4 group members
Project Requirements Change - If the requirements changed, we would be remap the project. | Unlikely | Problematic | We will be using the iterative model to an extent, so should the requirements change partway through the project, we should be able to accommodate for this.
Requirements are not well understood - We may not fully understand the task at hand from the beginning of the project. | Likely | Moderate | We do not expect to fully understand the task from the beginning of the project, so we will be using an iterative technique. This will allow us to continue learning and make changes to our project as we better understand the requirements.
Work takes longer than estimated in the project schedule - In the schedule, we mapped out an amount of time to spend on each piece of the project. It is possible we may not finish tasks in the anticipated amount of time. | Likely | Problematic | Should the work take us longer than expected, we will find time to free ourselves up for extra hours throughout the week to make sure we get the work completed.
Code grows too unorganized - As the code is edited time and time again, it will by nature slowly become harder and harder to understand. It is possible the code becomes incredibly too messy and can no longer be understood. | Possible | Severe | In the event that the code can no longer be understood, we will be forced to throw out our code and start over. To prevent this from happening, we will make sure to adhere to the coding standards set forth.