## Sheet1
Risk Assessment
By: Pavan K. Kottapalli
| Risk | Likelihood | Severity | Mitigation
| Data loss from personal computer - Each individual group member has their code on their personal computers. It is possible that a member may lose their code due to an error. | Possible | Low | All of our code is backed up and stored on GitHub. We will upload our code here regularly and be able to retrieve it anytime and use it incase we have any data loss issues.
| GitHub Servers go down - All of our code is stored on a Github repository, it would be unaccessable to us if the servers crashed. | Unlikely | Low | All of our invidiual code is stored on our personal computers. Each of the members will have access to all of their code incase the GitHub servers were to malfunction.
| Project requirements change - If the requirements of the project change. | Unlikely | Major | We will try to make our code as efficient as possible so that it can be peer reviewed and easily modified if there need to be any changes/modifcations.
| Requirements are not understood - We may not completely recognize the specific requirements of the project from the beginning. | Likely | Critical | We are constantly realizing new things that we need to do for the project. It is essential that we have a thorough understanding of the project at an early stage to ensure that we stay on track.
| Group member is unable to contribute - We have distributed the tasks of the project between 5 members. While it is unlikely, there is a chance that a member may fall sick or drop the class. | Unlikely | Major | All of the team members will have a basic understanding of each of the other group member's code so we can help each other out. If a group member drops the class, we will speak to Dr. Profeta and get advice on how we should proceed.
| We do not stick to schedule - We drew up an initial schedule using Gantt software. It is very likely that we will not stick to this schedule. | Likely | Major | If a part of the project takes longer than we perspected, we will make time during the week to ensure that the task is completed.